## Instructions
Construction daily report (site diary)
How to use this template
1. | Fill in one daily report per working day: crews, plant and equipment, delays, work performed, deliveries, visitors and incidents.
2. | Man-hours, lost hours, effective hours and utilization are calculated by the formulas in the shaded cells.
3. | Copy the totals of each day into the weekly summary and enter the hours before this week once, so the sheet keeps the running total since the start of the site.
4. | This file is an internal record; it does not replace a site diary or daily report that your contract or local rules require.
Everything you type stays in this file on your computer; nothing is sent anywhere.
Formula cells are locked without a password so they are not overwritten by mistake; to change them, use Review > Unprotect Sheet.
White cells: your entries
Shaded cells: formulas (locked)
Note
This file is a working aid. It does not replace your contract, the rules that apply to your project or the judgment of a qualified supervising engineer; check every figure before you rely on it.
Template: civilmanual.com, 25 Oct 2026

## Daily report
Construction daily report (site diary)
Project / site |  |  |  | Date
Weather
Temperature, morning (°F) | Temperature, noon (°F) | Temperature, evening (°F) | Precipitation | Wind | Weather note
Crews on site
Company | Trade | Workers | Hours per worker | Man-hours
Total
Plant and equipment
Plant | Number | Working hours each | Idle hours each | Working hours | Idle hours
Total
Delays and stoppages
Reason | Workers affected | Duration (h) | Lost man-hours
Total
Day totals
Workers on site
Gross man-hours
Lost man-hours
Effective man-hours
Utilization
Work performed
No. | Work performed
1
2
3
4
5
6
7
8
Deliveries
No. | Deliveries
1
2
3
4
5
Visitors and instructions
No. | Visitors and instructions
1
2
3
4
5
Incidents and near misses
Incident | Near miss | Description
Site manager |  |  | Supervising engineer or client representative
Name |  |  | Name
Signature |  |  | Signature
Date |  |  | Date
Note
This file is a working aid. It does not replace your contract, the rules that apply to your project or the judgment of a qualified supervising engineer; check every figure before you rely on it.
Template: civilmanual.com, 25 Oct 2026

## Weekly summary
Construction daily report (site diary): Weekly summary
Week starting (Monday)
Gross man-hours before this week
Effective man-hours before this week
Day | Date | Workers | Gross man-hours | Lost man-hours | Effective man-hours | Utilization | Gross since start | Effective since start
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday
Week total
Site manager |  |  |  | Supervising engineer or client representative
Name |  |  |  | Name
Signature |  |  |  | Signature
Date |  |  |  | Date
Note
This file is a working aid. It does not replace your contract, the rules that apply to your project or the judgment of a qualified supervising engineer; check every figure before you rely on it.
Template: civilmanual.com, 25 Oct 2026